## TimeLine_1
<<Institute Name>> |  |  |  | Project Timeline planning must list all the specific required tasks that are required achieve the functionalities described in system design. Tasks must be measurable.
<<Course>> <<No.of Semester>> Semester
Course Name: DSE10 Project Course Code: <<>>
Project Timeline Team No : A1
Sr. No | Project Task | Estimated Start Date | Estimated End Date
1 | Requirement Gathering
2 | Study of <<Name>> of ICT solution - 3 names
3 | Listing of general and distinict functionalities
| Total Days | <NN>
Declaration: I/We hereby declare that the timeline is prepared keeping in mind the complexity of each task and other aspects related to this project development. The duration planned is meant to be as close as the actual one.
| Enrollment No | Name | Signature
The tasks and deadlines are approved.
| Guide Name | Signature
Internal:

## Status_1
Shrimad Rajchandra Institute of Management and Computer Application
MCA 3 Semester
Course Name: DSE4 Project Course Code:040010405
Project Timeline Status Team No : 1
Sr. No | Project Task | Estimated Start Date | Estimated End Date
1 | Registration(viewer/Content creator/Ad Creator) | 16/01/2020 | 16/01/2020
2 | Login(viewer/Content creator/Ad Creator) | 17/01/2020 | 17/01/2020
3 | Manage Account(Viewer/Content creator/Adcreator) | 20/01/2020 | 21/01/2020
4 | Add Operators and assign permissions(Admin) | 22/01/2020 | 23/01/2020
5 | View Operators(Admin) | 24/01/2020 | 24/01/2020
6 | Manage Operator(Admin) | 25/01/2020 | 25/01/2020
7 | Create and manage news categories(Admin) | 27/01/2020 | 28/01/2020
8 | Display news category(viewer/content creator/ad creator) | 29/01/2020 | 30/01/2020
9 | Dashboard(Admin) | 31/01/2020 | 31/01/2020
10 | Create and manage FAQ(Admin) | 2020-01-02 | 2020-01-02
11 | Create & manage gallery(Admin) | 2020-03-02 | 2020-03-02
12 | Display gallery (Viewer) | 2020-04-02 | 2020-05-02
13 | Create & manage slideshow(Admin) | 2020-05-02 | 2020-05-02
14 | Dashboard(Operator) | 2020-06-02 | 2020-06-02
15 | Display slideshow(Viewer) | 2020-07-02 | 2020-10-02
16 | Verify news for approval(Operator) | 2020-11-02 | 13/2/2020
17 | Display news (viewer) | 14/2/2020 | 17/2/2020
18 | Verify ads for approval(Operator) | 18/2/2020 | 20/2/2020
19 | Display ads (viewer) | 20/2/2020 | 21/2/2020
20 | Dashboard(Content creator) | 22/2/2020 | 24/2/2020
21 | Create news(Content creator) | 25/2/2020 | 28/2/2020
22 | Manage Comment i.e. approve/dis-approve/spam(Content creator) | 2020-02-03 | 2020-04-03
23 | Manage news(Content creator) | 2020-05-03 | 2020-06-03
24 | Verify Content creator account for bank details for enabling monetization(Operator) | 2020-07-03 | 2020-07-03
25 | Verify Ad creator account for bank details for creating ads(Operator) | 2020-08-03 | 2020-08-03
26 | Send feedback(Content creator) | 2020-10-03 | 2020-10-03
27 | View FAQs (viewer/content creator/ad creator) | 2020-11-03 | 2020-11-03
28 | Display report of Content creator(Admin) 1. Popular content creator 2. Least popular content creator 3.Block Content creator | 2020-12-03 | 2020-12-03
29 | Display report of Ad creator(Admin) 1.Popular Ad creator 2.Least popular Ad creator 3.Block Ad creator | 13/3/2020 | 13/3/2020
30 | Display report of News(Admin) 1. Popular News 2. Total news 3. Block Ad creator | 14/3/2020 | 15/3/2020
31 | Display report of platform revenue(Admin) | 16/3/2020 | 16/3/2020
32 | Analyzing feedback for improvement(Opeator) | 16/3/2020 | 18/3/2020
33 | Replay the answer of queries creator(Operator) | 18/3/2020 | 18/3/2020
34 | Display query's answers (viewer/content creator/ad) | 19/3/2020 | 19/3/2020
35 | Enebling monetization of content creator based on specified criteria | 20/3/2020 | 20/3/2020
36 | Add bank details for earning(Content creator) | 21/3/2020 | 21/3/2020
37 | Withdraw revenue(Content creator) | 23/3/2020 | 23/3/2020
38 | View transaction report(Content creator) | 24/3/2020 | 27/3/2020
39 | Reports(Content creator) 1.Approve News 2.Cancel News 3.Active News 4.In-Active News | 27/3/2020 | 30/3/2020
40 | Dashboard(Ad creator) | 30/3/2020 | 31/3/2020
41 | Add bank details for publishing ads(Ad creator) | 2020-01-04 | 2020-01-04
42 | Create Ads(Ad creator) | 2020-02-04 | 2020-02-04
43 | Manage Ads(Ad creator) | 2020-03-04 | 2020-04-04
44 | Send feedback(Ad creator) | 2020-04-04 | 2020-04-04
45 | Deposite amount for deducting CPC amount from ads on per click(Ad creator) | 2020-04-04 | 2020-06-04
46 | View transaction report(Ad creator) | 2020-07-04 | 2020-07-04
47 | Reports(Ad creator) 1.Approve Ads 2.Cancel Ads 3.Runnig Ads | 2020-08-04 | 2020-10-04
48 | Performing action on news i.e. like/dislike/comment/report(Viewer) | 2020-11-04 | 2020-11-04
49 | Follow content creator(Viewer) | 2020-11-04 | 2020-12-04
50 | Recommending news to viewer | 13/4/2020 | 14/4/2020
51 | Ranking the content based on seo tag | 14/4/2020 | 15/4/2020
52 | Testing | 15/4/2020 | 20/4/2020
Declaration : The estimated dates are as per the timeline planning submitted. The actual dates are mentioned as the tasks have started and/or ended. The status is marked after appropriate verification.
|  | Enrollment No | Name
|  | 201904100120008 | Avinash G. Mishra
|  | 20190410020020 | Priyanka P. Patel
|  | 201904100120034 | Shabnam K. Siddiqui
|  | 201904100120048 | Jaimin A. Panchal
|  | Guide Name | Signature
Ms. Khushbu Patel